## XPULP_HW_LOOP
Requirement Location | Feature | Sub Feature | Feature Description | Verification Goal | Pass/Fail Criteria | Test-Program Type | UVM Test Config | Coverage Method | Test-Program Name | Link to Coverage | GVSOC ISS Status | GVSOC Witness (lane [config] verdetto gate) | GVSOC Note
CV32E40P User Manual - Chapter 12 | Hardware Loops | Hardware Loops Interrupts | HW Loop context should be saved in case of a context switchig event occuring | Demonstrate that HWLoop operation can be resumed after context switching if registers are correctly saved and restored when context switching occurs | Check against RM | Directed Self-Checking | see CV32E40Pv2_test_list.xlsx | Test Coverage |  | T: pulp_hwloop_interrupt_test__* T: corev_rand_pulp_hwloop_debug__* T: corev_rand_pulp_hwloop_debug_ebreak__* T: corev_rand_pulp_hwloop_debug_trigger__* T: corev_rand_pulp_hwloop_debug_trigger_with_ebreak__* T: corev_rand_pulp_hwloop_debug_with_interrupt__* T: corev_rand_pulp_hwloop_debug_with_int_debug_trigger__* T: corev_rand_pulp_hwloop_debug_with_int_debug_ebreak__* T: corev_rand_pulp_hwloop_debug_single_step__* T: corev_rand_pulp_hwloop_debug_trigger_with_single_step__* T: corev_rand_pulp_hwloop_debug_with_int_debug_trigger_and_ebreak__* T: corev_rand_pulp_hwloop_debug_with_int_debug_trigger_single_step__* T: corev_rand_pulp_hwloop_exception__* T: corev_rand_pulp_hwloop_exception_debug_trigger__* T: corev_rand_pulp_hwloop_exception_single_step_debug__* T: corev_rand_pulp_hwloop_exception_with_int_debug_trigger__* T: corev_rand_pulp_hwloop_illegal_instr_test__* | COVERED-GVSOC | pulp_hardware_loop_interrupt_test [pulp] PASS; corev_rand_pulp_hwloop_debug [pulp] PASS (+ebreak) | pulp_hwloop_interrupt_test__:IGNOTO corev_rand_pulp_hwloop_debug__:IGNOTO corev_rand_pulp_hwloop_debug_ebreak__:IGNOTO corev_rand_pulp_hwloop_debug_trigger__:IGNOTO corev_rand_pulp_hwloop_debug_trigge
|  |  | No specific limitations of when interrupt can occur | Core has received an interrupt at various locations of hardware loops, both in nested and single configurations, which includes for both loops : - first instruction address of the loop (lpstart) - next instruction after lpstart - Somewhere else in the loop - last instruction address before end of the loop (lpend) - last instruction address of the loop (lpend) | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage | corev_rand_pulp_hwloop_interrupt_test corev_rand_pulp_hwloop_debug_with_interrupt corev_directed_pulp_hwloop_test_with_interrupt corev_directed_pulp_hwloop_debug_with_interrupt corev_directed_pulp_hwloop_debug_with_int_debug_trigger corev_directed_pulp_hwloop_debug_with_int_debug_ebreak corev_directed_pulp_hwloop_debug_with_int_debug_trigger_and_ebreak corev_directed_pulp_hwloop_debug_with_int_debug_trigger_single_step | CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_irq_loc<single_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_irq_loc<single_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_irq_loc<single_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_irq_loc<single_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_irq_loc<single_hwloop,loc_others,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_irq_loc<nested_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_irq_loc<nested_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_irq_loc<nested_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_irq_loc<nested_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_irq_loc<nested_hwloop,loc_others,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_irq_loc<single_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_irq_loc<single_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_irq_loc<single_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_irq_loc<single_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_irq_loc<single_hwloop,loc_others,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_irq_loc<nested_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_irq_loc<nested_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_irq_loc<nested_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_irq_loc<nested_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_irq_loc<nested_hwloop,loc_others,*> | COVERED-GVSOC | corev_rand_pulp_hwloop_interrupt_test:QV corev_rand_pulp_hwloop_debug_with_interrupt:QV corev_directed_pulp_hwloop_test_with_interrupt:QV corev_directed_pulp_hwloop_debug_with_interrupt:QV corev_direc
|  |  |  | An interrupt occurs for every instruction of the loop, in both nested/non-nested configurations | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage |  | hwloop_interrupt_test | COVERED-CG | famiglia hwloop int/debug [pulp] PASS (12+ lane) | occorrenza per-istruzione = bin CG (F1); correttezza dal RM
|  |  | hardware loop feature could be used in interrupt routine/handler | Demonstrate that HWLoop can be interrupted, and another nested HWLoops can be executed in the interrupt handler | Check against RM | Directed Self-Checking | see CV32E40Pv2_test_list.xlsx | Testcase | pulp_hwloop_interrupt_test | T: pulp_hwloop_interrupt_test__* | COVERED-GVSOC | pulp_hardware_loop_interrupt_test:A/C1
|  | Hardware Loops Debug mode | No privileged instructions except for ebreak. The core can enter debug mode while executing instructions inside a hardware loop. No specific limitations on when the event can occur | - Enter in debug mode inside loop #0 and loop #1 in a non-nested configuration, single steps some instructions inside the loop, and then exit debug while in the loop - Enter in debug mode in nested configuration, outside inner loop, execute the first part of inner loop including setting instructions in single stepping, and exit debug mode while being in inner loop - Enter in debug mode in nested configuration, outside inner loop, execute the first part of inner loop including setting instructions in single stepping, and exit debug mode after having completed whole inner loop - In configurations described above, debug code can be executed, and the loop operations must resume normally afterwards | Check against RM | Directed Non-Self-Checking | see CV32E40Pv2_test_list.xlsx | Test Coverage |  | hwloop_debug_test | COVERED-CG | famiglia hwloop int/debug [pulp] PASS (12+ lane) | occorrenza per-istruzione = bin CG (F1); correttezza dal RM
|  |  |  | Core has entered in debug mode with debug request at various locations of hardware loops, both in nested and single configurations, which includes for both loops : - first instruction address of the loop (lpstart) - next instruction after lpstart - Somewhere else in the loop - last instruction address before end of the loop (lpend) - last instruction address of the loop (lpend) | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage | corev_rand_pulp_hwloop_test_with_random_debug corev_rand_pulp_hwloop_in_debug_rom corev_directed_pulp_hwloop_debug corev_directed_pulp_hwloop_test_with_random_debug | CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_haltreq_loc<single_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_haltreq_loc<single_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_haltreq_loc<single_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_haltreq_loc<single_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_haltreq_loc<single_hwloop,loc_others,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_haltreq_loc<nested_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_haltreq_loc<nested_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_haltreq_loc<nested_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_haltreq_loc<nested_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_haltreq_loc<nested_hwloop,loc_others,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_haltreq_loc<single_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_haltreq_loc<single_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_haltreq_loc<single_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_haltreq_loc<single_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_haltreq_loc<single_hwloop,loc_others,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_haltreq_loc<nested_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_haltreq_loc<nested_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_haltreq_loc<nested_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_haltreq_loc<nested_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_haltreq_loc<nested_hwloop,loc_others,*> | COVERED-GVSOC | corev_rand_pulp_hwloop_test_with_random_debug:QV corev_rand_pulp_hwloop_in_debug_rom:A/C2 corev_directed_pulp_hwloop_debug:A/C2 corev_directed_pulp_hwloop_test_with_random_debug:QV
|  |  |  | Core has entered in debug mode with ebreak instruction at various locations of hardware loops, both in nested and single configurations, which includes for both loops : - first instruction address of the loop (lpstart) - next instruction after lpstart - Somewhere else in the loop - last instruction address before end of the loop (lpend) - last instruction address of the loop (lpend) | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage | corev_rand_pulp_hwloop_debug_ebreak corev_directed_pulp_hwloop_debug_trigger_with_ebreak corev_directed_pulp_hwloop_debug_ebreak | CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_ebreakm_loc<single_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_ebreakm_loc<single_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_ebreakm_loc<single_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_ebreakm_loc<single_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_ebreakm_loc<single_hwloop,loc_others,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_ebreakm_loc<nested_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_ebreakm_loc<nested_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_ebreakm_loc<nested_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_ebreakm_loc<nested_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_ebreakm_loc<nested_hwloop,loc_others,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_ebreakm_loc<single_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_ebreakm_loc<single_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_ebreakm_loc<single_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_ebreakm_loc<single_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_ebreakm_loc<single_hwloop,loc_others,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_ebreakm_loc<nested_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_ebreakm_loc<nested_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_ebreakm_loc<nested_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_ebreakm_loc<nested_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_ebreakm_loc<nested_hwloop,loc_others,*> | COVERED-GVSOC | corev_rand_pulp_hwloop_debug_ebreak:QV corev_directed_pulp_hwloop_debug_trigger_with_ebreak:QV corev_directed_pulp_hwloop_debug_ebreak:QV
|  |  |  | Core has entered in debug mode with trigger at various locations of hardware loops, both in nested and single configurations, which includes for both loops : - first instruction address of the loop (lpstart) - next instruction after lpstart - Somewhere else in the loop - last instruction address before end of the loop (lpend) - last instruction address of the loop (lpend) | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage | corev_rand_pulp_hwloop_debug_trigger corev_directed_pulp_hwloop_debug_trigger_with_ebreak corev_directed_pulp_hwloop_debug_trigger | CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_trigger_loc<single_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_trigger_loc<single_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_trigger_loc<single_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_trigger_loc<single_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_trigger_loc<single_hwloop,loc_others,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_trigger_loc<nested_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_trigger_loc<nested_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_trigger_loc<nested_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_trigger_loc<nested_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_trigger_loc<nested_hwloop,loc_others,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_trigger_loc<single_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_trigger_loc<single_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_trigger_loc<single_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_trigger_loc<single_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_trigger_loc<single_hwloop,loc_others,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_trigger_loc<nested_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_trigger_loc<nested_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_trigger_loc<nested_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_trigger_loc<nested_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_trigger_loc<nested_hwloop,loc_others,*> | COVERED-GVSOC | corev_rand_pulp_hwloop_debug_trigger:QV corev_directed_pulp_hwloop_debug_trigger_with_ebreak:QV corev_directed_pulp_hwloop_debug_trigger:QV
|  |  |  | Core has single-stepped at various locations of hardware loops, both in nested and single configurations, which includes for both loops : - first instruction address of the loop (lpstart) - next instruction after lpstart - Somewhere else in the loop - last instruction address before end of the loop (lpend) - last instruction address of the loop (lpend) | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage | corev_rand_pulp_hwloop_debug_single_step corev_directed_pulp_hwloop_debug_trigger_with_single_step | CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_step_cnt_loc<single_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_step_cnt_loc<single_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_step_cnt_loc<single_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_step_cnt_loc<single_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_step_cnt_loc<single_hwloop,loc_others,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_step_cnt_loc<nested_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_step_cnt_loc<nested_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_step_cnt_loc<nested_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_step_cnt_loc<nested_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_dbg_step_cnt_loc<nested_hwloop,loc_others,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_step_cnt_loc<single_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_step_cnt_loc<single_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_step_cnt_loc<single_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_step_cnt_loc<single_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_step_cnt_loc<single_hwloop,loc_others,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_step_cnt_loc<nested_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_step_cnt_loc<nested_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_step_cnt_loc<nested_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_step_cnt_loc<nested_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_dbg_step_cnt_loc<nested_hwloop,loc_others,*> | COVERED-GVSOC | corev_rand_pulp_hwloop_debug_single_step:QV corev_directed_pulp_hwloop_debug_trigger_with_single_step:QV
|  |  |  | Enter/exit debug mode for every instruction of the loop, in both nested/non-nested configurations | Check against RM | Directed Non-Self-Checking | see CV32E40Pv2_test_list.xlsx | Test Coverage |  | hwloop_debug_test | COVERED-CG | famiglia hwloop int/debug [pulp] PASS (12+ lane) | occorrenza per-istruzione = bin CG (F1); correttezza dal RM
|  | Hardware Loops Exceptions | No specific limitations on when the event can occur | Core has encountered an exception at various locations of hardware loops, both in nested and single configurations, which includes for both loops : - first instruction address of the loop (lpstart) - next instruction after lpstart - Somewhere else in the loop - last instruction address before end of the loop (lpend) - last instruction address of the loop (lpend) This is valid for ebreak, ecall, illegal instructions exceptions. | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage | corev_rand_pulp_hwloop_exception corev_rand_pulp_hwloop_exception_debug_trigger corev_rand_pulp_hwloop_exception_single_step_debug corev_rand_pulp_hwloop_exception_with_int_debug_trigger | CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_excp_*_loc<single_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_excp_*_loc<single_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_excp_*_loc<single_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_excp_*_loc<single_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_excp_*_loc<single_hwloop,loc_others,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_excp_*_loc<nested_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_excp_*_loc<nested_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_excp_*_loc<nested_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_excp_*_loc<nested_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_excp_*_loc<nested_hwloop,loc_others,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_excp_*_loc<single_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_excp_*_loc<single_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_excp_*_loc<single_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_excp_*_loc<single_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_excp_*_loc<single_hwloop,loc_others,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_excp_*_loc<nested_hwloop,loc_lpstart,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_excp_*_loc<nested_hwloop,loc_lpstart_plus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_excp_*_loc<nested_hwloop,loc_lpend,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_excp_*_loc<nested_hwloop,loc_lpend_minus4,*> CG: .uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_excp_*_loc<nested_hwloop,loc_others,*> | COVERED-GVSOC | corev_rand_pulp_hwloop_exception:A/C2 corev_rand_pulp_hwloop_exception_debug_trigger:QV corev_rand_pulp_hwloop_exception_single_step_debug:QV corev_rand_pulp_hwloop_exception_with_int_debug_trigger:QV
|  | Hardware Loops nesting | Loop number 0 has higher priority than loop number 1 in a nested loop configuration, meaning that loop 0 represents the inner loop. | Demonstrates that both HWLoop can be used indepentently without nesting, and in case of nesting, that loop #0 has higher priority than loop #1 | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage | corev_rand_pulp_hwloop_test corev_directed_for_hwloop_covg_test | CP: uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.cp_hwloop_type.single_hwloop CP: uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.cp_hwloop_type.single_hwloop CP: uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.cp_hwloop_type.nested_hwloop CP: uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.cp_hwloop_type.nested_hwloop | COVERED-GVSOC | corev_rand_pulp_hwloop_test:A/C2 corev_directed_for_hwloop_covg_test:A/C2
|  | Hardware Loops Instructions limitations | All instructions except RVC, jumps, branch, memory ordering, mret, dret, ecall, wfi are allowed inside HWLoops | coverage: All allowed multicycle instructions have been executed while one HWLoop is active All allowed one-cycle instructions have been executed while one HWLoop is active | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage | corev_rand_pulp_hwloop_test corev_directed_for_hwloop_covg_test | CP: uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_0.ccp_hwloop_type_setup_insn_list CP: uvme_cv32e40p_pkg.uvme_rv32x_hwloop_covg__1.cg_features_of_hwloop_1.ccp_hwloop_type_setup_insn_list | COVERED-GVSOC | corev_rand_pulp_hwloop_test:A/C2 corev_directed_for_hwloop_covg_test:A/C2
| 4.4 Single step | Debug mode | Single stepping | all HWLoop instructions has been exectued in debug mode | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage | corev_rand_pulp_hwloop_debug_single_step corev_directed_pulp_hwloop_debug_single_step corev_rand_pulp_hwloop_test_with_random_debug | CP: uvme_cv32e40p_pkg.uvme_debug_covg.cg_debug_with_xpulp_inst.cr_xpulp_instructions_dbg_mode.< in_debug_mode,cv_setup0> CP: uvme_cv32e40p_pkg.uvme_debug_covg.cg_debug_with_xpulp_inst.cr_xpulp_instructions_dbg_mode.< in_debug_mode,cv_setup1> CP: uvme_cv32e40p_pkg.uvme_debug_covg.cg_debug_with_xpulp_inst.cr_xpulp_instructions_dbg_mode.< in_debug_mode,cv_setupi0> CP: uvme_cv32e40p_pkg.uvme_debug_covg.cg_debug_with_xpulp_inst.cr_xpulp_instructions_dbg_mode.< in_debug_mode,cv_setupi1> CP: uvme_cv32e40p_pkg.uvme_debug_covg.cg_debug_with_xpulp_inst.cr_xpulp_instructions_dbg_mode.< in_debug_mode,cv_count0> CP: uvme_cv32e40p_pkg.uvme_debug_covg.cg_debug_with_xpulp_inst.cr_xpulp_instructions_dbg_mode.< in_debug_mode,cv_count1> CP: uvme_cv32e40p_pkg.uvme_debug_covg.cg_debug_with_xpulp_inst.cr_xpulp_instructions_dbg_mode.< in_debug_mode,cv_counti0> CP: uvme_cv32e40p_pkg.uvme_debug_covg.cg_debug_with_xpulp_inst.cr_xpulp_instructions_dbg_mode.< in_debug_mode,cv_counti1> CP: uvme_cv32e40p_pkg.uvme_debug_covg.cg_debug_with_xpulp_inst.cr_xpulp_instructions_dbg_mode.< in_debug_mode,cv_start0> CP: uvme_cv32e40p_pkg.uvme_debug_covg.cg_debug_with_xpulp_inst.cr_xpulp_instructions_dbg_mode.< in_debug_mode,cv_start1> CP: uvme_cv32e40p_pkg.uvme_debug_covg.cg_debug_with_xpulp_inst.cr_xpulp_instructions_dbg_mode.< in_debug_mode,cv_starti0> CP: uvme_cv32e40p_pkg.uvme_debug_covg.cg_debug_with_xpulp_inst.cr_xpulp_instructions_dbg_mode.< in_debug_mode,cv_starti1> CP: uvme_cv32e40p_pkg.uvme_debug_covg.cg_debug_with_xpulp_inst.cr_xpulp_instructions_dbg_mode.< in_debug_mode,cv_end0> CP: uvme_cv32e40p_pkg.uvme_debug_covg.cg_debug_with_xpulp_inst.cr_xpulp_instructions_dbg_mode.< in_debug_mode,cv_end1> CP: uvme_cv32e40p_pkg.uvme_debug_covg.cg_debug_with_xpulp_inst.cr_xpulp_instructions_dbg_mode.< in_debug_mode,cv_endi0> CP: uvme_cv32e40p_pkg.uvme_debug_covg.cg_debug_with_xpulp_inst.cr_xpulp_instructions_dbg_mode.< in_debug_mode,cv_endi1> | COVERED-GVSOC | corev_rand_pulp_hwloop_debug_single_step:QV corev_directed_pulp_hwloop_debug_single_step:QV corev_rand_pulp_hwloop_test_with_random_debug:QV
CV32E40P User Manual - Chapter 13.2.2 | Hardware Loops CSRs | Hardware Loops CSRs | 0xCC0: lpstart0, 32-bit RW register, start address of HWloop0 0xCC4: lpstart1, 32-bit RW register, start address of HWloop1 0xCC1: lpend0, 32-bit RW register, end address of HWloop0 0xCC5: lpend1, 32-bit RW register, end address of HWloop1 0xCC2: lpcount0, 32-bit RW register, number of iterations of HWloop0 0xCC6: lpcount1, 32-bit RW register, number of iterations of HWloop1 number of instructions for loop 0 (nbInst0) is (lpend0 - lpstart0)/4 number of instructions for loop 1 (nbInst1) is (lpend1 - lpstart1)/4 | coverage: All bits of lpstart0 are toggled All bits of lpstart1 are toggled All bits of lpend0 are toggled All bits of lpend1 are toggled All bits of lpcount0 are toggled All bits of lpcount1 are toggled | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage |  | toggle waived | COVERED-CG | lane hwloop [pulp] PASS + CG uvme_rv32x_hwloop_covg; corev_rand_pulp_hwloop_count_range_test [pulp] PASS | correttezza dal RM; chiusura bin = asse UCDB (F1)
|  |  | HWLoop CSR Registers are readable using Zicsr read instructions | lpstart0 have been read lpstart1 have been read lpend0 have been read lpend1 have been read lpcount0 have been read lpcount1 have been read | Check against RM | Directed Self-Checking | see CV32E40Pv2_test_list.xlsx | Testcase | cv32e40pv2_illegal_ro_csr_access_test | T: cv32e40pv2_illegal_ro_csr_access_test__* | COVERED-GVSOC | cv32e40pv2_illegal_ro_csr_access_test:A/C1
|  |  | Illegal Exception Instruction is raised when using Zicsr write instructions on HWLoop registers | lpstart0 have been written lpstart1 have been written lpend0 have been written lpend1 have been written lpcount0 have been written lpcount1 have been written | Check against RM | Directed Self-Checking | see CV32E40Pv2_test_list.xlsx | Testcase | cv32e40pv2_illegal_ro_csr_access_test | T: cv32e40pv2_illegal_ro_csr_access_test__* | COVERED-GVSOC | cv32e40pv2_illegal_ro_csr_access_test:A/C1
CV32E40P User Manual - Chapter 18.3 | Hardware Loops Instructions | CV.STARTI | cv.starti L, uimmL lpstart[L] = PC + (uimmL << 2) Loads the lpstart[L] CSR register with current PC value plus an unsigned integer | input operands: uimmL value is any +ve, max and 1 for both loops (L value) | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage | corev_rand_pulp_hwloop_test | CP: RISCV_coverage_pkg.RISCV_coverage__1.cv_startii_cg.cp_L | COVERED-GVSOC | corev_rand_pulp_hwloop_test:A/C2
|  |  |  | coverage: All bits of uimmL are toggled | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage |  | toggle waived | COVERED-CG | lane hwloop [pulp] PASS + CG uvme_rv32x_hwloop_covg; corev_rand_pulp_hwloop_count_range_test [pulp] PASS | correttezza dal RM; chiusura bin = asse UCDB (F1)
|  | CV.START | cv.start L, rs1 lpstart[L] = PC + rs1 Loads the lpstart[L] CSR register with current PC value plus an unsigned integer | Register operands All possible rs1 registers are used. | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage | corev_rand_pulp_hwloop_test | CP: RISCV_coverage_pkg.RISCV_coverage__1.cv_start_cg.cp_rs1 | COVERED-GVSOC | corev_rand_pulp_hwloop_test:A/C2
|  |  |  | coverage: All bits of rs1 are toggled | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage |  | toggle waived | COVERED-CG | lane hwloop [pulp] PASS + CG uvme_rv32x_hwloop_covg; corev_rand_pulp_hwloop_count_range_test [pulp] PASS | correttezza dal RM; chiusura bin = asse UCDB (F1)
|  | CV.ENDI | cv.endi L, uimmL lpend[L] = PC + (uimmL << 2) Loads the lpend[L] CSR register with the current PC value plus an unsigned integer | input operands: uimmL value is any +ve, max and zero for both loops (L value) | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage | corev_rand_pulp_hwloop_test | CP: RISCV_coverage_pkg.RISCV_coverage__1.cv_endi_cg.cp_L | COVERED-GVSOC | corev_rand_pulp_hwloop_test:A/C2
|  |  |  | coverage: All bits of uimmL are toggled | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage |  | toggle waived | COVERED-CG | lane hwloop [pulp] PASS + CG uvme_rv32x_hwloop_covg; corev_rand_pulp_hwloop_count_range_test [pulp] PASS | correttezza dal RM; chiusura bin = asse UCDB (F1)
|  | CV.END | cv.end L, rs1 lpend[L] = PC + rs1 Loads the lpend[L] CSR register with the current PC value plus an unsigned integer | Register operands All possible rs1 registers are used. | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage | corev_rand_pulp_hwloop_test | CP: RISCV_coverage_pkg.RISCV_coverage__1.cv_end_cg.cp_rs1 CP: RISCV_coverage_pkg.RISCV_coverage__1.cv_end_cg.cp_L | COVERED-GVSOC | corev_rand_pulp_hwloop_test:A/C2
|  |  |  | coverage: All bits of rs1 are toggled | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage |  | toggle waived | COVERED-CG | lane hwloop [pulp] PASS + CG uvme_rv32x_hwloop_covg; corev_rand_pulp_hwloop_count_range_test [pulp] PASS | correttezza dal RM; chiusura bin = asse UCDB (F1)
|  | CV.COUNTI | cv.counti L, uimmL lpcount[L] = uimmL Loads the lpcount[L] CSR register with the given value | input operands: uimmL value is any +ve, max and 1 for both loops (L value) | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage | corev_rand_pulp_hwloop_test | CP: RISCV_coverage_pkg.RISCV_coverage__1.cv_counti_cg.cp_L | COVERED-GVSOC | corev_rand_pulp_hwloop_test:A/C2
|  |  |  | coverage: All bits of uimmL are toggled | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage |  | toggle waived | COVERED-CG | lane hwloop [pulp] PASS + CG uvme_rv32x_hwloop_covg; corev_rand_pulp_hwloop_count_range_test [pulp] PASS | correttezza dal RM; chiusura bin = asse UCDB (F1)
|  | CV.COUNT | cv.count L, rs1 lpcount[L] = op1 Loads the lpcount[L] CSR register with the given value | Register operands All possible rs1 registers are used for both loops (L value) | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage | corev_rand_pulp_hwloop_test | CP: RISCV_coverage_pkg.RISCV_coverage__1.cv_count_cg.cp_rs1 CP: RISCV_coverage_pkg.RISCV_coverage__1.cv_count_cg.cp_L | COVERED-GVSOC | corev_rand_pulp_hwloop_test:A/C2
|  |  |  | input operands: rs1 value is any +ve and 1 for both loops (L value) | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage | corev_rand_pulp_hwloop_test | CP: RISCV_coverage_pkg.RISCV_coverage__1.cv_count_cg.cp_rs1_maxvals.one CP: RISCV_coverage_pkg.RISCV_coverage__1.cv_count_cg.cp_rs1_sign.pos CP: RISCV_coverage_pkg.RISCV_coverage__1.cv_count_cg.cp_L | COVERED-GVSOC | corev_rand_pulp_hwloop_test:A/C2
|  |  |  | coverage: All bits of rs1 are toggled | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage |  | toggle waived | COVERED-CG | lane hwloop [pulp] PASS + CG uvme_rv32x_hwloop_covg; corev_rand_pulp_hwloop_count_range_test [pulp] PASS | correttezza dal RM; chiusura bin = asse UCDB (F1)
|  | CV.SETUPI | cv.setupi L, uimmL, uimmS lpstart[L] = PC + 4 lpend[L] = PC + (uimmS << 2) lpcount[L] = uimmL | input operands: uimmL value is any +ve, max and 1 for both loops (L value) uimmS value is 3 (min), +ve, max for both loops (L value) | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage | corev_rand_pulp_hwloop_test | CP: RISCV_coverage_pkg.RISCV_coverage__1.cv_setupi_cg.cp_L | COVERED-GVSOC | corev_rand_pulp_hwloop_test:A/C2
|  |  |  | coverage: All bits of uimmS are toggled for both loops (L value) All bits of uimmL are toggled for both loops (L value) | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage |  | toggle waived | COVERED-CG | lane hwloop [pulp] PASS + CG uvme_rv32x_hwloop_covg; corev_rand_pulp_hwloop_count_range_test [pulp] PASS | correttezza dal RM; chiusura bin = asse UCDB (F1)
|  | CV.SETUP | cv.setup L, rs1, uimmL lpstart[L] = PC + 4 lpend[L] = PC + (uimmL << 2) lpcount[L] = rs1 | Register operands All possible rs1 registers are used for both loops (L value) | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage | corev_rand_pulp_hwloop_test | CP: RISCV_coverage_pkg.RISCV_coverage__1.cv_setup_cg.cp_rs1 CP: RISCV_coverage_pkg.RISCV_coverage__1.cv_setup_cg.cp_L | COVERED-GVSOC | corev_rand_pulp_hwloop_test:A/C2
|  |  |  | input operands: uimmL value is +ve, max and zero rs1 value are min value (3), +ve and max value for both loops (L value) | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage | corev_rand_pulp_hwloop_test | CP: RISCV_coverage_pkg.RISCV_coverage__1.cv_setup_cg.cp_rs1_maxvals.max CP: RISCV_coverage_pkg.RISCV_coverage__1.cv_setup_cg.cp_rs1_sign.pos CP: RISCV_coverage_pkg.RISCV_coverage__1.cv_setup_cg.cp_L | COVERED-GVSOC | corev_rand_pulp_hwloop_test:A/C2
|  |  |  | coverage: All bits of uimmL are toggled for both loops (L value) | Check against RM | Constrained-Random | see CV32E40Pv2_test_list.xlsx | Functional Coverage |  | toggle waived | COVERED-CG | lane hwloop [pulp] PASS + CG uvme_rv32x_hwloop_covg; corev_rand_pulp_hwloop_count_range_test [pulp] PASS | correttezza dal RM; chiusura bin = asse UCDB (F1)
Note on I1: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : Check for Test Coverage naming
Note on K1: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : Temporary names
Note on D2: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : Not a feature to be verified, but a requirement to keep a functioning state
Note on G2: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : Moved from Non-self-checking to self-checking
Note on K2: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : Add all random tests as well
Note on E4: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : Current random tests can't reach this scenario Réponse : ccp_hwloop_type_irq_loc if ok Réponse : Unrealistic, see requirement above
Note on G5: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : Moved from Non-self-checking to self-checking
Note on E6: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : Replaced by clearer items below
Note on K6: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : Check with Pascal about pulp_hardware_loop_debug_test
Note on K12: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : First * means ebreak / ecall / illegal / mc_insn
Note on E14: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : For this, covers instructions met when lpcount0/1 > 0 AND lpstart0/1 < PC < lpend0/1
Note on D16: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : are mapped into the CSR custom *read-only* address, from v1.2.0 spec, p42 (HWLoop constraints
Note on E20: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : Missing in imperas coverage
Note on E31: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : Cross with hwloop L field is missing Réponse : Check with Mike his opinion about this

## DONOTDELETE
Pass/Fail Criteria | Test Type | Coverage Method
Self Checking Test | RISC-V Compliance | Testcase
Signature Check | OpenHW Compliance | Functional Coverage
Check against ISS | Directed Self-Checking | Assertion Coverage
Check against RM | Directed Non-Self-Checking | Code Coverage
Assertion Check | Constrained-Random | N/A
Any/All | ENV capability, not specific test
Other | Other
N/A | N/A

## GVSOC_provenance
GVSOC ISS parity annotation
Data audit | 2026-08-12
Reference model | GVSOC iss_v2 (RVVI DPI step-and-compare), sostituisce ImperasDV nella stessa TB
Revisione ISS | core 9f275f6f / pulp 66b648a / gvsoc 3401620 / gvsoc_rvvi f2a6adc / cvv 2b9d33a1d
Evidenza | quick_val full gate 2026-08-11: 155 PASS / 0 FAIL / 3 known-fail / 2 skip - evidenza /data2/marco.paci/validation-evidence/quickval_gate_20260811_c2/
Metodo | Colonne GVSOC affiancate al tracciamento originale; item-level da CV32E40Pv2_test_list + lane quick_val (160 lane, 4 config)